## Sheet1
DATE	FEEDBACK	PLAYING AS	DEPARTMENT	SEVERITY	FIXED BY	DATE FIXED	COMMENTS
05/03/2020	Lab floor is higher than the rest of the floors	Alien	Design		Kyle	13-Mar
05/03/2020	Alien is pretty slippery	Alien	Design
05/03/2020	Glass door trigger areas need checking as they’re very difficult to open	Alien	Design		Kyle	13-Mar
05/03/2020	Corridor from storage room to armoury has no colliders	Alien	Design		Kyle	Ages ago
05/03/2020	Signs are good :D	Alien	Design				thanks
05/03/2020	Need a “Room leads to room” signage	Alien	Design			13-Mar	I think this would remove the unknown factor of trying to find your way around a station while the alien is following you.
05/03/2020	Need signs above the corridors in the biosphere	Alien	Design			13-Mar	Moved signs to be better visible.
05/03/2020	Broken door animation looks good	Alien	Design				suprising
05/03/2020	Gen room door isn’t flush with the floor	Alien	Design		Kyle	13-Mar
05/03/2020	Alien moving up stairs is weird as they attach to the sides of the stairs	Alien	Programming
05/03/2020	Crosshair would probably be better than a dot	Alien	Design
05/03/2020	“Acid spit would be cool”	Alien	Prototype
05/03/2020	Gen room aliens can’t go from pillar to ceiling	Alien	Design
05/03/2020	Vents in the ceiling are difficult to get into	Alien	Design/ Programming
05/03/2020	Gen room pillar at the bottom can glitch alien movement due to complex geometry	Alien	Design		Kyle	13-Mar
05/03/2020	Gen room wall is clipped into entrance vent	Alien	Design		Kyle	13-Mar
05/03/2020	Broken office door clips through vent	Alien	Design		Kyle	When I redid vents
05/03/2020	Canteen vent entrance from gen room is badly aligned	Alien	Design		Kyle	When I redid vents
05/03/2020	A “Training area” to get used to controls would be good. Obstacle course for alien, firing range for marine	Alien	Prototype
05/03/2020	Vent T section near security room, gen room, and canteen is misaligned, causes alien to disconnect from venting	Alien	Design		Kyle	When I redid vents
05/03/2020	Canteen steps don’t work, colliders need checking	Alien	Design
05/03/2020	Holo table on the canteen balcony has a mesh collider and should use primitives	Alien	Design		Kyle	15-Mar
05/03/2020	Canteen pillar colliders need shrinking	Alien	Design		Kyle	15-Mar
05/03/2020	Railing bottom rung shouldn’t have a collider	Alien	Design
05/03/2020	Can’t climb up slanted tables as alien due to colliders not running all the way to the floor	Alien	Design		Kyle	15-Mar
05/03/2020	Rectangular tables I canteen have no underside	Alien	Design		john	31-Mar	They are glass, they aren't supposed too.
05/03/2020	Rectangular table leg visibly clipped into wall	Alien	Design		Kyle	15-Mar
05/03/2020	Door from canteen to bio, you can see through to space	Alien	Design		Kyle	15-Mar
05/03/2020	In canteen TV against wall is floating	Alien	Design		Kyle	15-Mar
05/03/2020	Canteen big wall panels in left corner next to bio door are not aligned	Alien	Design		john	31-Mar
05/03/2020	Jump takes a little practice to get used to, but did get used to it	Alien	Feedback
05/03/2020	Get hit by glass doors on opening them	Alien	Design
05/03/2020	No vents in office	Alien	Design		Kyle	When I redid vents
05/03/2020	Office right-most panel between glass doors has no collider	Alien	Design		Kyle	15-Mar
05/03/2020	Office detailed wall, can’t be transferred to from the other wall	Alien	Design		Kyle	15-Mar
05/03/2020	Office floor right of desk has lines between texture	Alien	Design		Kyle	15-Mar
05/03/2020	“Floor texture looks like minecraft sand” - did take an hour to notice this as alien	Alien	Feedback
05/03/2020	Storage room door to armoury is really badly aligned	Alien	Design		Kyle	15-Mar
05/03/2020	Other storage room door is open but renders as closed	Alien	Design
05/03/2020	Marine mouse sensitivity is too high	Marine	Feedback
05/03/2020	Assault rifle recoil is too jerky	Marine	Design
05/03/2020	Needs hint that oxygen will regenerate in the biosphere	Marine	Writing
05/03/2020	Control key shoots	Marine	Design		Eugene	11-Mar
05/03/2020	Recoil doesn’t return gun to where you shot from	Marine	Programming
05/03/2020	No crouch, jump or aim down sight	Marine	Design/ Programming
05/03/2020	Alien eggs aren’t visible through the broken door	Marine	Design
05/03/2020	Can’t walk into the security room due to door alignment	Marine	Design		Kyle	15-Mar
05/03/2020	Generator room stairs need a railing as you can get yourself stuck	Marine	Design
05/03/2020	Possible secondary – faster breaching	Marine	Prototype
05/03/2020	Rogue collider in spawn corridor floor allows marine to get air from walking forwards	Marine	Design		Kyle	15-Mar
05/03/2020	Need a sign above space-side door in spawn corridor	Marine	Design		Kyle	15-Mar
05/03/2020	Spawn corridor door not flush with the floor	Marine	Design		Kyle	15-Mar
05/03/2020	Oxygen regeneration area doesn’t cover the whole biosphere	Marine	Design		Kyle	15-Mar
05/03/2020	Player seems very tall in spawn corridor, flloor collider may be too high	Marine	Design
05/03/2020	Need an audio clip in the spawn corridor, saying something like “Depressurising”	Marine	Audio
05/03/2020	Effect in spawn corridor was obviously pressurisation	Marine	Feedback
05/03/2020	Sprint should use oxygen faster	Marine	Programming		Eugene	11-Mar
05/03/2020	Feels like you should be able to open doors from a little further away	Marine	Design		Eugene	11-Mar
05/03/2020	You can step up railings	Marine	Design/ Programming
05/03/2020	It isn’t obvious what to do in the security room, or that there are two of them	Marine	Design
05/03/2020	The security room button also isn’t obvious	Marine	Design		Kyle	31-Mar
05/03/2020	Need a UI element for a warning of low/ no oxygen	Marine	Design		Eugene	11-Mar
05/03/2020	Max O2 displays as 99 not 100	Marine	Programming		Eugene	11-Mar
24/03/2020	Can get stuck behind desk in alien spawn	Alien	Design		Kyle	27-Mar
24/03/2020	Controls are snapping and disorientating with alien	Alien	Design/Programming
24/03/2020	The snapping of the alien makes it difficult to engage in combat	Alien	Design/Programming
24/03/2020	More torch light is needed	Marine	Design		Kyle	27-Mar
24/03/2020	Marines move too fast	Marine	Design		Kyle	31-Mar
24/03/2020	Alien feels underpowered	Alien	Design		Kyle	27-Mar
24/03/2020	Oxygen is too low to complete the objective	Marine	Design		Kyle	27-Mar
24/03/2020	Difficult to tell when you have changed orientation in a vent as the alien	Alien	Programming
24/03/2020	Torch light should be softer	Marine	Design		Kyle	27-Mar
24/03/2020	You jump after going through a door	Alien/Marine	Design
24/03/2020	Red crosshair is hard to see	Alien/Marine	Design		Kyle	31-Mar
24/03/2020	Can get stuck underneath generator room	Alien/Marine	Design
24/03/2020	Generator room floor has collider issues that stops the marine from moving on the walkways	Marine	Design		Kyle	27-Mar
24/03/2020	Death screen needs to be added as unable to tell when you die	Alien/Marine	Design/ Programming
24/03/2020	Sliding marines leads to overshooting corridor entrances	Marine	Programming
24/03/2020	Time to kill the alien is too low	Alien	Design
24/03/2020	Red against black door opening radial dial is hard too see	Alien/Marine	Design		Kyle	31-Mar
24/03/2020	Biosphere door trigger area needs to be larger	Marine	Design		Kyle	27-Mar
24/03/2020	Permanent objective guidance should be on screen	Marine	Design/ Programming
24/03/2020	Breaching takes too long	Marine	Design		Kyle	31-Mar
24/03/2020	Alien jump needs a charge bar	Alien	Design/ Programming/Art
05/04/2020	Hole in office next to lab	Alien	Design
05/04/2020	Stuck spot in the table in alien spawn	Alien	Design		john	06/04/2020
05/04/2020	Spwans sometimes spawn in space	Marine	Design/Programing
05/04/2020	ADS problem where when right clicking as marine the players contol is given to another player including the alien and other marine. WSAD and mouse were given to serprate players although this happened only once out of 6 games	Marine	Programming		harry	06/04/2020
05/04/2020	Audio is heard at the same volume across the hole map even when miles away when fallen through the floor	Marine	Programming?
05/04/2020	Players recommend an audio slider	Alien/marine	Design/programming
05/04/2020	Able to fall through the floor in alien spawn near the table	Alien	Design		john	06/04/2020
05/04/2020	Unable to go into the biosphere from the marine spawn corridor	Marine	Design		kyle	06/04/2020
05/04/2020	game has minor lag on low end laptops (wow who knew)	Both	Design

25/04/2020	Alien is able to interact with marine objectives		Programming
25/04/2020	Torch position needs to be changed as it casts the marines shadow in from of them		Design		Kyle
25/04/2020	Torch lights the whole of the canteen		Design		Kyle
25/04/2020	Torch light doesn’t sync across net, can’t see others torches		Programming
25/04/2020	Esc key resets graphics options		Programming
25/04/2020	Gen room alien can get stuck between railing and wall		Design		Kyle	27/04/20
25/04/2020	Door under canteen stairs shuts instantly		Design/ Programming
25/04/2020	Health can go negative		Programming
25/04/2020	Air needs to be flagged as being able to regen in biosphere.		Design		Kyle
25/04/2020	Flag when air gets low		Design
25/04/2020	Too easy as alien to switch surface, could have to hold button to switch		Programming
25/04/2020	Having to spend 5 seconds opening a door makes you feel vulnerable but is dull (I think ignore, that’s kinda the point – H)		Design		Kyle
25/04/2020	Objectives are unclear, text was missed on first run throguh		Design
25/04/2020	Possible collision errors with canteen stairs and marine		Programming
25/04/2020	Alien selection in lobby is quite subtle, ccould be more obvoius		Programming
25/04/2020	Text at bottom on marine briefing needs to be around longer		Design/ Programming
25/04/2020	Door opening is inconsistent, sometimes doesn’t work		Programming
25/04/2020	Once out of ammo removes a lot of agency for marine – could have ammo regen in armoury and flag this		Design
25/04/2020	Doors could auto open once they’ve been opened once? (I think leave them – H)		Design
25/04/2020	Security room off of genny, moving left while looking at switch yeets you out of ceiling		Design		Kyle
25/04/2020	Spatial sound doesn’t exist		Programming
25/04/2020	Sign text is too small		Design
25/04/2020	Flag that two switches need to be pressed from generator room, prompt is unclear		Design
25/04/2020	Flag when the allien does emergency regen for both alien and marine		Programming/ Design
25/04/2020	Alien looks like its moving even when it isn’t due to networking		Programming
25/04/2020	Could add a free air refil to marines in gen/ switch rooms after activating switches??		Design
25/04/2020	Aliens view ability doesn’t work		Programming