## Sheet1
DATE	FEEDBACK	PLAYING AS	DEPARTMENT	SEVERITY	FIXED BY	DATE FIXED
05/03/2020	Lab floor is higher than the rest of the floors	Alien	Design		Kyle	13-Mar
05/03/2020	Alien is pretty slippery	Alien	Design
05/03/2020	Glass door trigger areas need checking as they’re very difficult to open	Alien	Design		Kyle	13-Mar
05/03/2020	Corridor from storage room to armoury has no colliders	Alien	Design		Kyle	Ages ago
05/03/2020	Signs are good :D	Alien	Design		thanks
05/03/2020	Need a “Room leads to room” signage	Alien	Design		I think this would remove the unknown factor of trying to find your way around a station while the alien is following you.	13-Mar
05/03/2020	Need signs above the corridors in the biosphere	Alien	Design		Moved signs to be better visible.	13-Mar
05/03/2020	Broken door animation looks good	Alien	Design		suprising
05/03/2020	Gen room door isn’t flush with the floor	Alien	Design		Kyle	13-Mar
05/03/2020	Alien moving up stairs is weird as they attach to the sides of the stairs	Alien	Programming
05/03/2020	Crosshair would probably be better than a dot	Alien	Design
05/03/2020	“Acid spit would be cool”	Alien	Prototype
05/03/2020	Gen room aliens can’t go from pillar to ceiling	Alien	Design
05/03/2020	Vents in the ceiling are difficult to get into	Alien	Design/ Programming
05/03/2020	Gen room pillar at the bottom can glitch alien movement due to complex geometry	Alien	Design
05/03/2020	Gen room wall is clipped into entrance vent	Alien	Design
05/03/2020	Broken office door clips through vent	Alien	Design
05/03/2020	Canteen vent entrance from gen room is badly aligned	Alien	Design
05/03/2020	A “Training area” to get used to controls would be good. Obstacle course for alien, firing range for marine	Alien	Prototype
05/03/2020	Vent T section near security room, gen room, and canteen is misaligned, causes alien to disconnect from venting	Alien	Design
05/03/2020	Canteen steps don’t work, colliders need checking	Alien	Design
05/03/2020	Holo table on the canteen balcony has a mesh collider and should use primitives	Alien	Design
05/03/2020	Canteen pillar colliders need shrinking	Alien	Design
05/03/2020	Railing bottom rung shouldn’t have a collider	Alien	Design
05/03/2020	Can’t climb up slanted tables as alien due to colliders not running all the way to the floor	Alien	Design
05/03/2020	Rectangular tables I canteen have no underside	Alien	Design
05/03/2020	Rectangular table leg visibly clipped into wall	Alien	Design
05/03/2020	Door from canteen to bio, you can see through to space	Alien	Design
05/03/2020	In canteen TV against wall is floating	Alien	Design
05/03/2020	Canteen big wall panels in left corner next to bio door are not aligned	Alien	Design
05/03/2020	Jump takes a little practice to get used to, but did get used to it	Alien	Feedback
05/03/2020	Get hit by glass doors on opening them	Alien	Design
05/03/2020	No vents in office	Alien	Design
05/03/2020	Office right-most panel between glass doors has no collider	Alien	Design
05/03/2020	Office detailed wall, can’t be transferred to from the other wall	Alien	Design
05/03/2020	Office floor right of desk has lines between texture	Alien	Design
05/03/2020	“Floor texture looks like minecraft sand” - did take an hour to notice this as alien	Alien	Feedback
05/03/2020	Storage room door to armoury is really badly aligned	Alien	Design
05/03/2020	Other storage room door is open but renders as closed	Alien	Design
05/03/2020	Marine mouse sensitivity is too high	Marine	Feedback
05/03/2020	Assault rifle recoil is too jerky	Marine	Design
05/03/2020	Needs hint that oxygen will regenerate in the biosphere	Marine	Writing
05/03/2020	Control key shoots	Marine	Design		Eugene	11-Mar
05/03/2020	Recoil doesn’t return gun to where you shot from	Marine	Programming
05/03/2020	No crouch, jump or aim down sight	Marine	Design/ Programming
05/03/2020	Alien eggs aren’t visible through the broken door	Marine	Design
05/03/2020	Can’t walk into the security room due to door alignment	Marine	Design
05/03/2020	Generator room stairs need a railing as you can get yourself stuck	Marine	Design
05/03/2020	Possible secondary – faster breaching	Marine	Prototype
05/03/2020	Rogue collider in spawn corridor floor allows marine to get air from walking forwards	Marine	Design
05/03/2020	Need a sign above space-side door in spawn corridor	Marine	Design
05/03/2020	Spawn corridor door not flush with the floor	Marine	Design
05/03/2020	Oxygen regeneration area doesn’t cover the whole biosphere	Marine	Design
05/03/2020	Player seems very tall in spawn corridor, flloor collider may be too high	Marine	Design
05/03/2020	Need an audio clip in the spawn corridor, saying something like “Depressurising”	Marine	Audio
05/03/2020	Effect in spawn corridor was obviously pressurisation	Marine	Feedback
05/03/2020	Sprint should use oxygen faster	Marine	Programming		Eugene	11-Mar
05/03/2020	Feels like you should be able to open doors from a little further away	Marine	Design		Eugene	11-Mar
05/03/2020	You can step up railings	Marine	Design/ Programming
05/03/2020	It isn’t obvious what to do in the security room, or that there are two of them	Marine	Design
05/03/2020	The security room button also isn’t obvious	Marine	Design
05/03/2020	Need a UI element for a warning of low/ no oxygen	Marine	Design		Eugene	11-Mar
05/03/2020	Max O2 displays as 99 not 100	Marine	Programming		Eugene	11-Mar